## Sheet1
# | Name | Time (hr) | Notes | Developer
1 | Property ID reference |  | Property view page needs to built. It does already exists but (I think) it only lists the address right now. We should build a table that displays all the data (inc. inspection times?). Should this page only be viewable if it is not rented? | Michael
3 | Viewing Times |  | Create a table something like this: property_views(id, property_id, start_datetime, end_datetime, staff_id). Create this table by adding to the install.php script. Then copy the contracts.php create/edit/delete method. It should be reasonably similar. | Jason
4 | Property Inspection Registration |  | Create a table property_view_tenants(property_id, tenant_id). Again, copy the contracts.php file as it would be similar | Jason
7 | Staff Property Allocation |  | Pretty sure this is done already?
8 | Property Assignment View |  | Copy the properties.php table which displays the list of properties in the system. Add a select box to the webpage and then modify the SQL query to do something like WHERE staff_id=$_GET['staffID'] | Michael
10 | Separation of Duties |  | We'll do this last (ref: #16). Check for user_type and user_id in the $_SESSION array to determine what they can see. | Jake
13 | Website search refinement |  | On the home page, where the search feature is, add a few more textboxes which say 'suburb', 'street' and select boxes like 'number of bedrooms', etc. modify the SQL appropriately. ALSO, the properties create/edit/delete and database table needs to be updated to include number_of_(bedrooms¦bathrooms¦carports) | Michael
14 | Property Photo Gallery |  | Create a database table using install.php; property_images(id, property_id, URL_to_image). Google search PHP file upload. Shouldn't be too difficult. Create a section in the property view page which finds all the images assigned to a property and display them. Also show a picture on the search results page? | Jason
15 | Property Inspection Request |  | Create a new file called something like contact.php. Add a form which accepts an email, subject and message. When you click submit, make it print out 'We have received your email, etc'. But don’t actually do anything with the email | Michael
16 | User Login |  | Modify the existing login to allow the operator to select what type of user they are logging in as (staff, tenant, owner). If it david, his username is david then we know its david, regardless of what type of user the operator selects. Save the user_type and user_id in the $_SESSION variable. | Jake
17 | User Registration |  | same as login but registration, instead of login | Jake